## activity
Activity | Time allocation (hours)
Thursday meeting | 1 per week = 31
Proofread Introduction & Methods | 3
Proofread Results: Remote sensing review | 2
Proofread Results: Government Collaboration | 2
Proofread Results: Tool Implementation | 2
Proofread Final Draft | 5
Total | 45

## gantt
Task | Subtask | Week
|  | 1/2 | 3/4 | 5/6 | 7/8 | 9/10 | 11/12 | 13/14 | 15/16 | 17/18 | 19/20 | 21/22 | 23/24 | 25/26 | 27/28 | 29/30 | 31/32
Proposal | bar: Week 1/2 to Week 7/8
Machine Learning (ML) methods | Implementation of ML Methods | bar: Week 9/10 to Week 13/14
Running ML methods with test data | bar: Week 13/14 to Week 17/18
Validation ML methods | bar: Week 19/20 to Week 23/24
Develop tool | bar: Week 19/20 to Week 31/32
Stay Aruba | Stay dates | bar: Week 11/12 to Week 23/24
Familiarize organization | bar: Week 11/12 to Week 13/14
Take diverse vegetation pictures | bar: Week 11/12 to Week 13/14
Conduct interviews | bar: Week 15/16 to Week 19/20
Colaboration Aruban Government | Develop Interviews | bar: Week 9/10 to Week 11/12
Conduct interviews | bar: Week 15/16 to Week 19/20
User reflection of developed tool | bar: Week 19/20 to Week 23/24
Report | Introduction | bar: Week 9/10 to Week 13/14
Methods | bar: Week 9/10 to Week 11/12
Results Machine Learning methods | bar: Week 11/12 to Week 15/16
Results Vegetation classification | bar: Week 15/16 to Week 19/20
Results tool implementation | bar: Week 19/20 to Week 23/24
Discussion | bar: Week 23/24 to Week 27/28
Conclusion | bar: Week 23/24 to Week 27/28
Finalization | Edit and Review | bar: Week 27/28 to Week 29/30
Presentation | bar: Week 29/30 to Week 31/32

## RQs
Research Question | Methodology
1) Which of the machine learning classification methods of Support Vector Machines (SVMs), Random Forests (RF) and regular and boosted Decision Trees (DTs) computed can most accurately map worldCover classes in Aruba? | Programming using Google Earth Engine
2) Are worldCover classes satisfactory and in monitoring arubas environment or are | Interviews with government stakeholders
3) Can land cover classification help aid the DNM? If so, for which purposes specifically? | Interviews with government stakeholders
4) Which of the machine learning classification methods of Support Vector Machines (SVMs), Random Forests (RF) and regular and boosted Decision Trees (DTs) computed can most accurately map local vegetation classes in Aruba? | Programming using Google Earth Engine
5) What are the differences in accuracy between computing local vegetation classes and international vegetation classes using remote sensing data and machine learning methods for Aruba? | Programming in python using scikit and Google Earth Engine

## dates
Acivity | Deadline
Starting date | 2023-11-13
Proposal Deadline | 11/12/2023 (4 weeks from start)
Introducto & Methods draft | 2024-01-29
Results RS review draft | 2024-02-26
Result DNM Collaboration | 2024-03-25
Results Tool implementation | 2024-04-22
Draft | 2024-05-27
Final Deadline | 24/06/2024 (31 weeks after start)
Preferred Defence date | 28/06/2024 (31.5 weeks after start)

## Vegetation, name to number
1 | Agave ¦ Agave ¦
2 | Aloe ¦ Aloe vera ¦
3 | Almendron ¦ Terminalia catappa ¦ India almond
4 | Appeldam ¦ Ziziphus spina-christi ¦
5 | Banana di rif ¦ Sesuvium portulacastrum ¦
6 | Barba di yoncuman ¦ Albizia lebbeck ¦
7 | Barbarita ¦ Strumpfia maritima ¦
8 | Basora blanco ¦ Bastardia viscosa ¦
9 | Basora preto ¦ Cordia curassavica ¦ Black sage
10 | Batata di lama ¦ Ipomoea pes-caprae ¦ Ivy
11 | Batata di porco ¦ Boerhavia coccinea ¦
12 | Beishi ¦ Solanum americanum ¦
13 | Beishi di baranca ¦ Stenostomum acutatum ¦
14 | Beishi di Lama ¦ Crossopetalum rhacoma ¦
15 | Bembe ¦ Portulaca oleracea ¦
16 | Betonica ¦ Melochia Tomentosa ¦
17 | Beyisima ¦ Antigonon leptopus ¦
18 | Bonchi di lama ¦ Canavalia rosea ¦ Beach Bean
19 | Bonchi totolica ¦ Crotalaria retusa ¦ Large Yellow Rattlebox
20 | Brakgras ¦ Sporobolus pyramidatus ¦
21 | Brakuha, Brak gras marga ¦ Sporobolus virginicus ¦
22 | Brazil, Brasia, Kampeshi, Brasil ¦ Haematoxylum brasiletto ¦
23 | Breba ¦ Cereus repandus ¦
24 | Breba blanco ¦ ¦
25 | Breba di pushi ¦ Pilosocereus lanuginosus ¦
26 | Bringamosa ¦ Cnidoscolus urens ¦
27 | Brusca ¦ Senna occidentalis ¦
28 | Brusca dushi ¦ Senna bicapsularis ¦
29 | Buffelgras ¦ Cenchrus ciliaris ¦
30 | Bushi (curvispinus) ¦ Melocactus curvispinus ¦
31 | Bushi (macracanthos) ¦ Melocactus macracanthos ¦
32 | Bushi (stramineus) ¦ Melocactus stramineus ¦
33 | Bushi (x bozsingianus) ¦ Melocactus x bozsingianus ¦
34 | Bushi di sero geel (e tin color geel) ¦ ¦
35 | Bushicuri ¦ Morisonia americana ¦
36 | Buzugua ¦ Morinda royoc ¦
37 | Cabey di negro ¦ Lithophila muscoides ¦
38 | Cadushi ¦ Stenocereus griseus ¦
39 | Cadushi surnam ¦ Euphorbia lactea ¦
40 | Cadushi??? ¦ Lernaireocereus griseus ¦
41 | Calalu ¦ Amaranthus dubius ¦
42 | Calalu di porco ¦ Amaranthus polygonoides ¦
43 | Calbas ¦ Crescentia cujete ¦ Calabash
44 | Camari ¦ Coccoloba swartzii ¦
45 | Carpata ¦ Ricinus communis ¦
46 | Catuna ¦ Gossypium hirsutum ¦
47 | Catunbom ¦ Calotropis procera ¦ Giant milkweed
48 | Cawara blanco ¦ Cordia dentata ¦ White manjack
49 | Chanana ¦ Evolvulus convolvuloides ¦
50 | Chanana ¦ Ludwigia erecta ¦
51 | Chloris barbata ¦ Chloris barbata ¦
52 | Coco di amina macho ¦ Cyperus confertus ¦
53 | Coco di amina? ¦ Cyperus esculentus ¦
54 | Cocolode ¦ Heliotropium indicum ¦
55 | Cocolode shimaron ¦ Heliotropium curassavicum ¦
56 | Cocorobana ¦ Tournefortia gnaphalodes ¦
57 | Concomber shimaron ¦ Cucumis anguria ¦
58 | Cordon di San Fransisco ¦ Cryptostegia grandiflora ¦
59 | Coriente ¦ Achyranthes aspera ¦
60 | Coushati ¦ Krugiodendron ferreum ¦
61 | Cucuisa, Cuco di indjan ¦ Agave arubensis ¦
62 | Cucuisa, pita di trankera ¦ Agave karatto ¦
63 | Curahout ¦ Peltophorum acutifolium ¦
64 | Cushicuri ¦ Acanthocereus tetragonus ¦ Triangle cactus
65 | Cyperus ligularis ¦ Cyperus ligularis ¦
66 | Dabaruida ¦ Pithecellobium unguis-cati ¦
67 | Druif ¦ Coccoloba uvifera ¦ Sea grape
68 | Druif Surnam ¦ Syzygium cumini ¦
69 | Egletes prostata ¦ Egletes prostrata ¦
70 | Elefante?, olefante? ¦ Polygala violacea ¦
71 | Ficus ¦ Ficus benjamina ¦
72 | Flor di bruid ¦ ¦
73 | Flor di sanger ¦ Lantana camara ¦
74 | Flor scondi ¦ Phyllanthus amarus ¦
75 | Fofoti / Mangel blanco ¦ Conocarpus erectus ¦
76 | Foyo di crus ¦ Thespesia populnea ¦
77 | Funfun ¦ Corchorus hirsutus ¦ Jackswitch
78 | Funfun muhe ¦ Corchorus orinocensis ¦ Orinoco jute
79 | Garoti di San Jose ¦ Leucaena leucocephala ¦ Jumbie Bean
80 | Gran Beshi ¦ Celtis iguanaea ¦ Iguana hackberry
81 | Horea di raton ¦ Callisia repens ¦
82 | Hubada ¦ Vachellia tortuosa ¦
83 | Huliba ¦ Quadrella odoratissima ¦
84 | Huliba macho ¦ Capparis indica ¦
85 | hunagato / hunja hunja ¦ pithecellobium platylobum ¦
86 | Hunjagato, hunja hunja ¦ Sphinga platyloba ¦
87 | huri-huri ¦ huri-huri ¦
88 | Janje zwemt ¦ Pistia stratiotes ¦
89 | Johnson gras?, Djoin gras? ¦ Sorghum halepense ¦
90 | Kachiu?, kuchua?, kuchiu? Dam machu?, Tam machu? ¦ Clusia rosea ¦
91 | Kamille shimaron ¦ Lippia nodiflora ¦
92 | Kaya-Kaya ¦ Arivela viscosa ¦ Asian spiderflower
93 | Kedebeshi ¦ Capparis linearis ¦
94 | Kelki blauw ¦ ¦
95 | Kenepa ¦ Melicoccus bijugatus ¦
96 | Kiviti ¦ Croton niveus ¦
97 | Klap ¦ Physalis cordata ¦
98 | Kwihi ¦ Prosopis juliflora ¦
99 | Lamoenchi ¦ ¦
100 | Lantana arubensis ¦ Lantana arubensis ¦
101 | Las nueve ¦ ¦
102 | Laseis ¦ Tephrosia cinerea ¦
103 | Laseis, Yerba di seis? ¦ Indigofera suffruticosa ¦
104 | Leli di San Jose ¦ ¦
105 | Lenga di baca ¦ Lactuca intybacea ¦
106 | Lisdodel ¦ Typha domingensis ¦
107 | Loki loki ¦ Phyllanthus botryanthus ¦
108 | Macubari ¦ Guapira pacurero ¦
109 | Magdalena blanco ¦ Catharanthus roseus ¦
110 | Magdalena di Seru Pretu, Magdalena ¦ Isocarpha oppositifolia ¦
111 | Mahawa ¦ Ficus brittonii ¦
112 | Maishi di totolica preto?, paragras? ¦ Urochloa mollis ¦
113 | Maishi di totolica shimaron? ¦ Echinochloa colona ¦
114 | Maishi grandi ¦ Zea mays ¦
115 | Maishi grandi Shimaron ¦ Commelina erecta ¦
116 | Maishi rabo ¦ Sorghum vulgare ¦
117 | Maishi, Maishi rabo ¦ Sorghum bicolor ¦
118 | makurá ¦ abrus precatorius ¦
119 | Mampurito ¦ Porophyllum ruderale ¦
120 | Mangel Preto ¦ Avicennia Germinans ¦
121 | Mangel shimaron ¦ Laguncularia Racemosa ¦
122 | Mangel Tam ¦ Rhizophora mangle ¦
123 | Mango ¦ Mangifera indica ¦ Mango Tree
124 | Mansaniya bobo, mansalinja macho, mansaniya macho ¦ Metopium brownei ¦
125 | Manzaliña ¦ Hippomane mancinella ¦
126 | Maraca ¦ Crotalaria incana ¦
127 | Marengo ¦ Moringa oleifera ¦
128 | Mari di palu ¦ Cynanchum boldinghii ¦
129 | Maripampun ¦ Matelea rubra ¦
130 | Mata combles ¦ Schoepfia schreberi ¦
131 | Mata di cachu? Yerba di cangrew? ¦ Boerhavia scandens ¦
132 | Mata di kawara spaño ¦ Cordia sebestena ¦ Geiger Tree
133 | Mata di pisca ¦ Jacquinia arborea ¦ Braceletwood
134 | Mata di yuana ¦ Bourreria succulenta ¦
135 | mata pisca of mata di pisca ¦ Jacquina armillaris ¦
136 | Mata potlood ¦ Euphorbia tirucalli ¦
137 | Mispel ¦ Manilkara zapota ¦ Sapodilla
138 | Moli moli ¦ Physalis pubescens ¦
139 | Molimoli, Klapchi ¦ Physalis angulata ¦
140 | morning glory ¦ jacquemontia cumanensis ? ¦
141 | Mosterd, stoki ¦ Capparis flexuosa ¦
142 | Batata di zumbi ¦ Ceratosanthes palmata ¦
143 | Neem ¦ Azadirachta indica ¦
144 | Noni ¦ Morinda citrifolia ¦
145 | Oleifi ¦ Bonita daphnoides ¦ Olive Bush
146 | Orkidia di mondi, Orkidia ¦ Brassavola nodosa ¦
147 | Otaheiti ¦ Thespesia populnea ¦
148 | Pal'i siya blanco ¦ Bursera karsteniana ¦
149 | Pal'i siya cora ¦ Bursera simaruba ¦
150 | Pal'i siya dushi ¦ Bursera tomentosa ¦
151 | Palmita ¦ Hyphaene thebaica ¦ Duom palm
152 | Palo cayente, Burachi ¦ Pilocarpus goudotianus ¦
153 | Palo di Boneiro, Boneiro ¦ Casearia tremula ¦
154 | Palo di Boonchi ¦ Erythrina velutina ¦ Red Bean Tree
155 | Palo di coco ¦ Cocos nucifera ¦ Coconut Palm
156 | Palo di colebra ¦ Maytenus sieberiana ¦
157 | Palo di lechi ¦ Sideroxylon obovatum ¦
158 | Paragras? ¦ Urochloa mutica ¦
159 | Pataka?, rais di pataka? ¦ Cissampelos pareira ¦
160 | Patia shimaron ¦ Solanum agrarium ¦
161 | Pega-pega ¦ Kalanchoe houghtanni ¦
162 | Pegasaya ¦ Cenchrus echinatus ¦
163 | Pegasaya bobo ¦ Cenchrus pilosus ¦
164 | Pepeshi, Pega pega ¦ Mentzelia aspera ¦
165 | Pia di galinja ¦ Eleusine indica ¦
166 | Pia di galinja? Shimaron ¦ Digitaria ciliaris ¦
167 | Pitiseli machu, pitiseli shimaron, seleri shimaron ¦ Bidens cynapiiflia ¦
168 | Polbo shimaron ¦ Argemone mexicana ¦
169 | Rabo di cabai ¦ Tournefortia volubilis ¦
170 | Raspa cora, Statie? ¦ Stachytarpheta boldinghii ¦
171 | Ratonero ¦ Gliricidia sepium ¦
172 | Rauvolfia viridis ¦ Rauvolfia viridis ¦ Milk tree
173 | Ravolfia viridis ¦ Ravolfia viridis ¦ milky bush
174 | Reseda ¦ Lawsonia inermis ¦
175 | resida ¦ resida ¦
176 | Rosita? ¦ Hisbiscus phoeniceus ¦
177 | Salachi (blanco) ¦ Batis maritima ¦
178 | Scaevola plumieri ¦ Scaevola plumieri ¦ Borbon
179 | Scaevola taccada ¦ Scaevola taccada ¦
180 | Scobiyo ¦ Scoparia annua ¦
181 | Scopet ¦ Ruellia tuberosa ¦
182 | Sea Peas ¦ Canavalia maritima ¦
183 | Seida ¦ Jatropha gossypiifolia ¦
184 | Seida Cora flaria ¦ n/a ¦
185 | Senebla ¦ Senna italica ¦
186 | Senebla ¦ Senna obovata ¦
187 | Shimarucu ¦ Malpighia emarginata ¦
188 | Shoshoro ¦ Passiflora foetida ¦
189 | Silver bottonwood ¦ Conocarpus erectus sericeus ¦
190 | Stakamahachi? ¦ Rivina humilis ¦
191 | Stoki ¦ Cynophalla flexuosa ¦
192 | Strena di canto di lama? ¦ Sophora tomentosa ¦
193 | Supi / asufro ¦ Pereskia guamacho ¦
194 | Suriana Maritimo ¦ Suriana maritima ¦ Bay cedar
195 | Tabaco ¦ Nicotiana tabacum ¦
196 | Taki ¦ Geoffroea spinosa ¦
197 | Tamarijn ¦ Tamarindus indica ¦ Tamarind
198 | Tanchi ¦ Capraria biflora ¦
199 | Tarabara ¦ Mimosa distachya ¦
200 | Taya ¦ Erithalis fruticosa ¦
201 | Tebenki ¦ Pectis febrifuga ¦
202 | Tebenki macho ¦ Pectis linifolia ¦
203 | Tebenki muhe ¦ Pectis prostrata ¦
204 | Teco ¦ Bromelia humilis ¦
205 | Tete di cacho ¦ Gundlachia corymbosa ¦ Horse-bush
206 | tete di porco ¦ tete di porco ¦
207 | Tomati shimaron ¦ ¦
208 | Torojil ¦ Torojil ¦
209 | Toronjil ¦ Melissa officinalis ¦
210 | Tres or ¦ Abutilon hirtum ¦
211 | Trompet ¦ Ipomoea nil ¦
212 | Tuna ¦ Opuntia caracassana ¦
213 | Tuna di baca ¦ Opuntia elatior ¦
214 | Tuna di colebra ¦ Opuntia curassavica ¦
215 | Tuna surnam ¦ ¦
216 | Turnera ulmifolia ¦ Turnera ulmifolia ¦
217 | Unja di diabel, una di diabel ¦ Martynia annua ¦
218 | Walishali ¦ Croton flavens ¦
219 | Wanglo ¦ Tribulus cistoides ¦ Jamaican feverplant
220 | Wanglo bobo, Anglo bobo ¦ Kallstroemia curta ¦
221 | Wanglo bobo, anglo bobo? ¦ Kallstroemia pubescens ¦
222 | Warero ¦ Cissus sicyoides ¦
223 | Warero crus ¦ Cissus trifoliata ¦
224 | Warero, wareru, Kabuya di trankera ¦ Cissus verticillata ¦
225 | Watapana ¦ Caesalpinia coriaria ¦
226 | Watapana shimaron ¦ Chamaecrista nictitans ¦
227 | Waterhyacint ¦ Eichhorniacrassipes ¦
228 | Wayaca ¦ Guaiacum officinale ¦
229 | Wayaca macho, wayaca shimaron ¦ Guaiacum sanctum ¦
230 | Yambo shimaron? ¦ Malachra alceifolia ¦
231 | Yerba chico ¦ Evolvulus antillanus ¦ Morning Glory
232 | Yerba di biento (macho)? ¦ Chloris virgata ¦
233 | Yerba di cabai ¦ Tillandsia flexuosa ¦
234 | Yerba di cabrito, basora di liber ¦ Parthenium Hysterophorus ¦
235 | Yerba di coco ¦ Cyperus rotundus ¦
236 | Yerba di coneu ¦ Portulaca halimoides ¦
237 | Yerba di coneu (macho)/ Bembe shimaron ¦ Portulaca elatior ¦
238 | Yerba di cusinchi ¦ ¦
239 | Yerba di fuku? ¦ Sida spinosa ¦
240 | Yerba di ginete? ¦ Digitaria californica ¦
241 | Yerba di glas, trompet ¦ Ipomoea incarnata ¦
242 | Yerba di kanja, yerba di sinta ¦ Thalassia testudinum ¦
243 | Yerba di krabo? ¦ Croton lobatus ¦
244 | Yerba di kuchu ¦ Cyperus planifolius ¦
245 | Yerba di lagadishi ¦ Rhynchosia minima ¦
246 | Yerba di lama ¦ ¦
247 | Yerba di lechi ¦ Euphorbia dioeca ¦
248 | Yerba di lechi muhe?, yerba di lechi homber? ¦ Eurphorbia maculata ¦
249 | Yerba di pia di galiña ¦ Chloris barbata ¦
250 | Yerba di pinda ¦ Sida Ciliaris ¦
251 | Yerba di Sali ¦ Heliotropium ternatum ¦
252 | Yerba di salo ¦ Stemodia maritima ¦
253 | Yerba di San Nicolas? ¦ Paspalum laxum ¦
254 | Yerba di sero ¦ Croton ovalifolius ¦
255 | Yerba di soldachi ¦ Euphorbia mesembryanthemifolia ¦
256 | Yerba di strea ¦ Fimbristylis cymosa ¦
257 | Yerba di vruminga, Pasota ¦ Chenopodium ambrosioides ¦
258 | Yerba stijf ¦ ¦
259 | Yerba stinki ¦ Datura inoxia ¦
260 | Yerbe di cangreu ¦ Elytraria imbricata ¦
261 | Yerbe di coneu ¦ Portulaca venezuelensis ¦
262 | yerbe di coupa ¦ Cleome gynandra ¦
263 | Yuca amara, yuca guajira, yuca di mondi ¦ Manihot carthaginensis ¦
264 | Zeekraal ¦ Salicornia perennis ¦
265 | Zjiron ¦ Crateva tapia ¦ Gally pear , Grand cosmaya
266 | Caoba ¦ Swietenia macrophylla ¦ Mahogany
267 | Pink Poui ¦ Tabebuia rosea ¦
268 | Cordia Bullata ¦
269 | Bonchi strena ¦ Parkinsonia aculeata
270 | Kibrahacha ¦ Tabebuia Billbergii
271 | Syringodium filiforme ¦ Manatee grass
272 | Halophila stipulacea ¦ Halophila seagrass
273 | Halimeda incrassata ¦ Three finger leaf alga
274 | Avrainvillea longicaulis ¦ Paddle blade algae
275 | Halodule wrightii ¦ Shoal grass
276 | Halophila baillonis
277 | Halophila decipiens
278 | Halophila engelmannii
279 | Cakile lanceolata ¦ Coastal Searocket
280 | Cyperus amabilis